## Project life cycle
| Autonomous Robotic Arm | [5 empty] | Project start: | [7 empty] | 2024-02-26
| Coast Institute of Technology | Project life cycle |  |  |  |  | Display week: | [7 empty] | 1
[7 empty] | 2024-02-26 | [6 empty] | 2024-03-04 | [6 empty] | 2024-03-11 | [6 empty] | 2024-03-18 | [6 empty] | 2024-03-25 | [6 empty] | 2024-04-01 | [6 empty] | 2024-04-08 | [6 empty] | 2024-04-15
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2024-02-26 to 2024-04-21
 | time axis 2024-02-26 to 2024-04-21
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Planning phase
| Define project scope,objectives and deliverables | Msao John | 100% | 2024-02-26 | 2024-02-29 | 4
| Identify key stakeholders and establish communication channels | Linsey Nyambura | 100% | 2024-02-29 | 2024-03-03 | 4
| Develop a project timeline and budget | Nichodemus Mwiki | 100% | 2024-03-03 | 2024-03-06 | 4
| Conduct risk assessment and develop mitigation strategies | Brian Wambui | 100% | 2024-03-06 | 2024-03-08 | 3
Design Phase
| Design the physical structure | Samuel Muuo | 100% | 2024-03-08 | 2024-03-12 | 5
| Selection and integration of sensors,actuators and control systems | Brian Wambui | 100% | 2024-03-12 | 2024-03-16 | 5
| Design of software architecture and user interface | Msao John | 100% | 2024-03-16 | 2024-03-19 | 4
| Conduct feasibility studies and prototyping | Linsey Nyambura | 100% | 2024-03-19 | 2024-03-21 | 3
Development phase
| Fabrication of the robotic arm components | Nichodemus Mwiki | 98% | 2024-03-21 | 2024-03-24 | 4
| Develop and test software algorithms | Linsey Nyambura | 90% | 2024-03-24 | 2024-03-27 | 4
| Integrate hardware and software components | Samuel Muuo | 85% | 2024-03-27 | 2024-03-31 | 5
| Implement safety features | Brian Wambui | 78% | 2024-03-31 | 2024-04-02 | 3
| Conduct risk assessment at each stage | Msao John | 69% | 2024-04-02 | 2024-04-07 | 6
Testing and validation phase
| Conduct rigorous testing of the robotic arm in controlled environments | Linsey Nyambura | 61% | 2024-04-07 | 2024-04-08 | 2
| Evaluate prerfomance metrics | Msao John | 57% | 2024-04-08 | 2024-04-09 | 2
| Conduct simulated trials | Nichodemus Mwiki | 50% | 2024-04-10 | 2024-04-12 | 3
| Gaher feedback from end-users and stakeholders | Samuel Muuo | 46% | 2024-04-12 | 2024-04-15 | 4
Development and training phase
| Prepare the robotic arm for deployment in the manufacturing facility | Samuel Muuo | 30% | 2024-04-15 | 2024-04-16 | 6
| Provide training to operators and maintenance staff | Nichodemus Mwiki | 19% | 2024-04-16 | 2024-04-18 | 5
| Develop documentation | Brian Wambui | 3% | 2024-04-18 | 2024-04-20 | 6
Formulas:
Display week: = [Display week:, row below]